## Hoja1
| Nov | Dic | Enero | Feb | Marzo | Abril | Mayo | Junio | Julio | Ago | Sept | Oct
Year 1 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Experiment One
Recruitment | x | x | x
Implement Online experiment |  | x | x | x
Data Análisis |  |  |  |  | x | x | x
Write paper | [5 empty] | x | x | x | x
Present at International Conference | [7 empty] | x
Present results at Universidad de Concepción (internal dissemination) | [11 empty] | x
Experiment two
Experiment design | [8 empty] | x | x | x | x
Coding | [11 empty] | x
Year 2
Expriment one (cont.)
Present results at Santiago based universities (e.g. FAE at USACH, and the ICP at PUC) | x | x |  |  |  |  | x
Present results at BEEC |  |  | x
Edit manuscript and send out for review | x | x | x | x | x | x
Revise and resubmit | [5 empty] | x | x | x | x | x | x | x
Experiment two (cont.)
Design | x
coding (cont.) |  | x
Pre-tests |  |  | x | x | x
Recruitment | [5 empty] | x | x | x | x | x
Running experiments | [6 empty] | x | x | x | x
Data Análisis | [9 empty] | x | x | x
Year 3
Experiment two (cont.)
Data Analysis | x | x
Write paper |  | x | x |  | x | x | x | x
Present results at IMBESS | [6 empty] | x
Edit manuscript and send out for review | [8 empty] | x | x | x | x
Dissemination Events in Santiago (2) | [6 empty] | x |  | x
Dissemination event in Valdivia | [7 empty] | x